## Summary
Estimate — TT-AIM-SPRINT-8C (20h Technical Analysis)
Project: | TT-AIM-SPRINT-8C
Total Budget: | 20 hours
Date: | 2026-03-17
Based on: | Estimate-TankTerminals-TT-AIM-SPRINT-8C-v1.xlsx
Phase | Hours
1. Environment Setup | 4
2. Code & Architecture Review | 7
3. Feature Strategy Evaluation | 5
4. Risk Assessment & Mitigation | 2.5
Reporting | 1.5
TOTAL | 20

## Detailed Breakdown
Task | Hours
PHASE 1: ENVIRONMENT SETUP
Access and review source code (PHP, React, Python) | 1
Set up local dev environment (PHP/Slim, React, Python) | 1.5
Restore database snapshot and connect services | 1
Verify system starts and key workflows function | 0.5
Subtotal Phase 1 | 4
PHASE 2: CODE & ARCHITECTURE REVIEW
Review PHP/Slim API codebase structure | 1.5
Review React JS frontend architecture | 1
Review Python LPB application and data pipeline | 1
Database schema analysis | 1.5
Map external integrations (Stripe, ReCaptcha, APIs, email) | 1
Infrastructure & deployment review | 1
Subtotal Phase 2 | 7
PHASE 3: FEATURE STRATEGY EVALUATION
TT-2436: Security & anti-abuse (login tracking, CSRF, ReCaptcha) | 0.5
TT-2439: LPB / Python pipeline (berth data, asset classes) | 0.75
TT-2434: Subscription splitting (Stripe vs non-Stripe) | 0.5
TT-2423: Logical Checks Dashboard (30 rules engine, tabs) | 1.25
TT-2444: Rhine CPP API (gasoil/gasoline data, API exposure) | 0.25
TT-2435: Ship & Terminal Modal (factsheet, map, responsive) | 1
TT-2443: Historical Waiting Times (data pipeline) | 0.25
Cross-ticket dependency analysis | 0.5
Subtotal Phase 3 | 5
PHASE 4: RISK ASSESSMENT & MITIGATION
Stripe integration & subscription data migration risks | 0.5
Rules engine scalability & dashboard performance (TT-2423) | 0.5
Python LPB pipeline change impact (TT-2439) | 0.25
Security implementation gaps (CSRF, ReCaptcha, abuse) | 0.25
Mobile/responsive UI constraints (TT-2435) | 0.25
Define mitigation strategies and testing approach | 0.75
Subtotal Phase 4 | 2.5
REPORTING
Compile findings into technical analysis report | 0.75
Prepare prioritized implementation roadmap | 0.5
Review and finalize deliverables | 0.25
Subtotal Reporting | 1.5
GRAND TOTAL | 20

## Tickets Reference
# | Ticket | Title | Original Est. (h)
1 | TT-2436 | Implement measures AI misuse | 12
2 | TT-2439 | Improvement LPB for BargeInsights: Tanker Type specific LPB stats | 20
3 | TT-2434 | Split Logistical Benchmarking (Non-Stripe subscriptions) | 3.5
4 | TT-2423 | Logical Checks Dashboard | 58.5
5 | TT-2444 | Rhine CPP: Low and High, make available in API | 4
6 | TT-2435 | Improvement on Ship and Terminal Modal | 64
7 | TT-2443 | Process Historical Waiting Times Data | TBD
|  | Total development hours | 162