## Commercial (Met meerwerk)
COMMERCIAL PRESENTATION
Description | Hrs | Split | Rate | Amount
Design & Development
Requirements analysis | 24.3 | 10% | 27.5 | 668.25
UI/UX design | 8.1 | 5% | 27.5 | 222.75
Architecture & detailed design | 16.2 | 10% | 27.5 | 445.5
Frontend & Backend | 162 | 100% | 27.5 | 4455
Total development | 210.6 | 115% | 27.5 | 5791.5
Quality Control & Deployment
Development Testing | 24.3 | 15% | 24 | 583.2
Unit test & quality improvement | 0 | 0% | 25.75 | 0
Deployment Stage & Production | 8.1 | 10% | 38.5 | 311.85
Transition & acceptance | 8.1 | 10% | 38.5 | 311.85
Regression Testing |  | 0% | 24 | 0
Dev server |  |  |  | 93
Total QC & Deployment | 40.5 | 35% | 32.0963 | 1299.9
Total direct production | 251.1 |  |  | 7091.4
Project management | 16.2 | 10% | 38.5 | 623.7
Project Time Material Budget | 267.3 |  |  | 7715.1
Fixed Pricing Risk | 0 | 0% |  | 0 |  | Cost of work | Margin | Margin AF/BA (50%) | Invoice AF to BA | Invoice | Status
Project Fixed Price Budget | 267.3 |  | 28.8631 | 7715.1 |  | 6370.2 | 1344.9
[5 empty] | Deposit (50%) | 3185.1 |  |  | 3185.1
|  |  |  | 7715.1 | Betaling bij oplevering | 3185.1 | 1344.9 | 672.45 | 3857.55
[8 empty] | Total for AIMFIRST VN | 7042.65

## Estimate
ESTIMATION SHEET
Project: | TT-AIM-SPRINT 8B
Updated date: | 15/1/2026
Updated by: | Phuc Le
SUMMARY
Implementation effort | 162
Duration | 5 weeks | (Tentative schedule)
PROJECT ACTIVITIES |  | GANTT CHART (WEEK)
Activity | Ratio | W1 | W2 | W3 | W4 | W5
Requirements analysis | 10% | x | x | x | x | x
UI/UX design | 5% | x | x | x | x | x
Architecture & detailed design | 10% | x | x | x | x | x
Deployment environment Stage / Production | 10% |  |  |  | x | x
Implementation | 100% | x | x | x | x | x
Quality control | 15% |  |  | x | x | x
Transition & acceptance | 10% |  |  |  | x | x
Project management | 10% | x | x | x | x | x
TEAM STRUCTURE
Role | Count
DEV React JS | 1 | 100% | 100% | 100% | 100% | 100%
Backend dev (PHP) | 2 | 100% | 100% | 100% | 100% | 100%
Python dev | 1
QA | 1 |  | 100% | 100% | 100% | 100%
Devops | 1 |  | 5% | 5% | 5% | 5%
PM | 1 | 10% | 10% | 10% | 10% | 10%
7
ASSUMPTIONS

## CostOf Wok
No | Title | Total hours | Rate | Total
1 | Development (Implementation) PHP | 162 | 22 | 3564
3 | UI/UX design | 8.1 | 22 | 178.2
4 | Architecture & detailed design | 16.2 | 22 | 356.4
5 | Requirements analysis | 16.2 | 22 | 356.4
6 | Quality control | 24.3 | 20 | 486
7 | Project Manager | 16.2 | 25 | 405
8 | Deployment (Devops) | 16.2 | 24 | 388.8
9 | Transition & acceptance | 16.2 | 22 | 356.4
Total |  | 275.4 |  | 6091.2
| Dev Server fee | 3 | 93 | 279
Total billing |  |  |  | 6370.2

## FunctionalitiesBreakdown
FUNCTIONALITIES BREAKDOWN TT-AIM-SPRINT-8C (8 tickets)
No. | Ticket number | Title | Breadown task | Estimate (hours) | Note
1 | TT-2436 | Implement measures AI misuse | Deactivate subscription when abnormal usage is registered: - Tracked user login : 1hr - Count the number of times the user logs in and the factsheet visited to deactivate : 1hr - Display message: account deactivated: 1h - Define the deactivate option for each user and check it when the user logs in: 1hr | 4
|  |  | Provide a warning signal in case of high usage: - send notify email : 1hr - Create notification: 1hr | 2
|  |  | Implement ReCaptcha for page | 4
|  |  | Add CSRF token for form | 2
2 | TT-2439 | Improvement LPB for BargeInsights: Tanker Type specific LPB stats | Change 1: instead of update the Python LPB app, we can update berth historical data function (Slim API) for ‘visits’, ‘visit duration’, and ‘waiting time’ : 4hrs | 4
|  |  | Change 2 : update Python LPB app can run with all aset classes | 8
|  |  | Change 3 & change 4 | 8
3 | TT-2434 | Split Logistical Benchmarking in Logistical Performance and Product Flows as Non Stripe subscriptions | Implement User story 1: 1. Non-Stripe Changes : 0.5hrs 2. Stripe Subscriptions: 0.5hrs 3. Subscription Inclusion Rules: 0.5hrs 4. Update old data (All existing non-Stripe users who currently have Logistical Benchmarking and therefore access to Product Flows): 1hr 5, Improvement on BI Package: 1hr | 3.5
4 | TT-2423 | Logical Checks Dashboard | User story 1: Logical Checks dashboard | 0.5
|  |  | User story 2: Label classifications | 2
|  |  | User story 3: Logical Check Rules | 2
|  |  | User story 4: Logical check dashboard: - Render layout : -- Tab 1: 2hrs -- Tab 2: 4hrs -- Edit terminal : 6hrs - Execute Rules (has 30 rules) --> 32 hours - Approving and Revoking approved a Warning --> 1 hour - Check the approved warning in the Rule --> 1 hour | 46
|  |  | User story 5 | 8
5 | TT-2444 | Rhine CPP: Low and High and make available in API | - Back Office – Gasoil - Back Office – Gasoiline - API requirements | 4
6 | TT-2435 | Improvement on Ship and Terminal Modal | User story 0 : Improvement of Terminal factsheet information | 16 | The current platform UI is desktop-optimized and not designed for mobile responsive layouts. For TT-2435 we propose implementing adaptive panel behavior for smaller laptop screens only. Full mobile responsiveness would require a larger UI refactor outside the scope of this ticket.
|  |  | User story 1: Access detailed terminal information from the map | 24
|  |  | User story 2: Access Logistical Performance with berth overview widget | 12
|  |  | User story 3: Access detailed ship information from the map and Past route | 12
7 | TT-2443 | Process Historical Waiting Times Data
Development hours |  |  |  | 162
3