## Commercial (Met meerwerk)
COMMERCIAL PRESENTATION
Description | Hrs | Split | Rate | Amount
Technical Analysis & Discovery
Environment Setup | 4 |  | 27.5
Code & Architecture Review | 7 |  | 27.5
Feature Strategy Evaluation | 5 |  | 27.5
Risk Assessment & Mitigation | 2.5 |  | 27.5
Reporting | 1.5 |  | 27.5
Total Technical Analysis
Project Time Material Budget
Fixed Pricing Risk |  | 0
Project Fixed Price Budget

## Estimate
ESTIMATION SHEET
Project: | TT-AIM-SPRINT-8C (20h Technical Analysis)
Updated date: | 17/3/2026
Updated by:
SUMMARY
Total analysis effort | 20
Duration | 1 week
PROJECT PHASES
Phase | Hours
1. Environment Setup | 4
2. Code & Architecture Review | 7
3. Feature Strategy Evaluation | 5
4. Risk Assessment & Mitigation | 2.5
5. Reporting | 1.5
TOTAL
TECHNOLOGY STACK
Frontend | React JS
Backend | PHP (Slim API framework)
Data/Analytics | Python (LPB application)
Payments | Stripe integration
Infrastructure | Staging + Production environments
ASSUMPTIONS
Source code access (Git), database snapshot, and staging environment are provided
Original estimate and ticket descriptions are accurate and current
The 20h analysis covers discovery only — implementation is scoped separately at 162h+
DELIVERABLES
1. Working local development environment
2. Architecture overview (codebase, database, infrastructure, integrations)
3. Per-ticket implementation strategy recommendation
4. Risk register with mitigation strategies
5. Prioritized implementation roadmap

## CostOf Work
No | Title | Total hours | Rate | Total
1 | Technical Analysis (Senior Developer) | 20 | 22
Total